## Bugs
Defect # | Status | Raised By | Tested on Version | TestCase Id | Steps to Reproduce | Expected Results | Actual Results | Priority | Severity
1 | Open | Ann | v1 | TC_RT_02 | 1. Enter special characters in Name Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Name cannot have special characters" is shown | A message "Register is successful" is shown. | Medium | Low
2 | Open | Ann | v1 | TC_RT_03 | 1. Enter a numberic value in Name Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Name cannot have numbers" is shown | A message "Register is successful" is shown. | Medium | Low
3 | Open | Ann | v1 | TC_RT_05 | 1. Enter a value with spaces in Username Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Username cannot have spaces" is shown | A message "Register is successful" is shown. | Medium | Low
4 | Open | Ann | v1 | TC_RT_06 | 1. Enter special characters in Username Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Username cannot have special characters" is shown | A message "Register is successful" is shown. | Medium | Low
5 | Open | Ann | v1 | TC_RT_11 | 1. Enter a non-numberic value in Phone Number Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Phone number must be numeric" is shown | A message "Register is successful" is shown. | Medium | Low
6 | Open | Ann | v1 | TC_RT_12 | 1. Enter a value with spaces in Phone Number Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Phone number cannot have spaces" is shown | A message "Register is successful" is shown. | Medium | Low
7 | Open | Ann | v1 | TC_RT_14 | 1. Enter year above current year with spaces in Phone Number Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Year value must be less than current year" is shown | A message "Register is successful" is shown. | Medium | Low
8 | Open | Ann | v1 | TC_RT_17 | 1. Enter a value with spaces in Password Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Password cannot have spaces" is shown | A message "Register is successful" is shown. | Medium | Low
9 | Open | Ann | v1 | TC_RT_19 | 1. Enter a value different of Password Field in Re-enter password Field 2. Enter valid data for other fields 3. Click Sign up button | An error message "Re-enter password must be the same as Password" | A message "Register is successful" is shown. | High | Medium
10 | Open | Ann | v1 | TC_FP_01 | 1. Do not enter a value in Email field 3. Press Rest password button | An error message "Please fill out email" is shown | PHPMailer\PHPMailer\Exception: Invalid address: (to): #3 {main} | High | Major
11 | Open | Ann | v1 | TC_FP_03 | 1. Enter an unregistered email in Email field 3. Press Rest password button | An error message "Email is not registered" is shown | PHPMailer\PHPMailer\Exception: SMTP Error: Could not authenticate. in | High | Major
12 | Open | Ann | v1 | TC_FP_04 | 1. Enter a registered email in Email field 3. Press Rest password button | Email with new password is sent to user's email | PHPMailer\PHPMailer\Exception: SMTP Error: Could not authenticate. in | High | Major
13 | Open | Ann | v1 | TC_AM_02 | 1. Enter special characters in Name Field 2. Press Save button | An error message "Name cannot have special characters" is shown | A message "Updating successful" is shown | Medium | Low
14 | Open | Ann | v1 | TC_AM_03 | 1. Enter a numberic value in Name Field 2. Press Save button | An error message "Name cannot have numbers" is shown | A message "Updating successful" is shown | Medium | Low
15 | Open | Ann | v1 | TC_AM_05 | 1. Enter a value with spaces in Username Field 2. Press Save button | An error message "Username cannot have spaces" is shown | A message "Updating successful" is shown | Medium | Low
16 | Open | Ann | v1 | TC_AM_06 | 1. Enter special characters in username Field 2. Press Save button | An error message "Username cannot have special characters" is shown | A message "Updating successful" is shown | Medium | Low
17 | Open | Ann | v1 | TC_AM_11 | 1. Enter a value with non-numeric characters in Phone number Field 2. Press Save button | An error message "Phone number must be numeric" is shown | A message "Updating successful" is shown | Medium | Low
18 | Open | Ann | v1 | TC_AM_12 | 1. Enter a value with spaces in Phone number field 2. Press Save button | An error message "Phone number cannot have spaces" is shown | A message "Updating successful" is shown | Medium | Low
19 | Open | Ann | v1 | TC_AM_13 | 1. Enter a vyear value above current year in Date of Birth Field 2. Press Save button | An error message "Year value must be less than current year" is shown | A message "Updating successful" is shown | Medium | Low
20 | Open | Ann | v1 | TC_SS_03 | 1. Click on the search bar 2. Enter the non existing song's name 3. Press Enter or Search button | A message "Cannot find the song" should be displayed in the search results | A message "0 results" is displayed in the search results | Low | Low
21 | Open | Ann | v1 | TC_SS_06 | 1. Click on the search bar 2. Enter the non existing artist's name 3. Press Enter or Search button | A message "Cannot find the song" should be displayed in the search results | A message "0 results" is displayed in the search results | Low | Low
22 | Open | Ann | v1 | TC_SS_09 | 1. Click on the search bar 2. Enter the non existing album's name 3. Press Enter or Search button | A message "Cannot find the song" should be displayed in the search results | A message "0 results" is displayed in the search results | Low | Low